## PMR
SCHOOLS DIVISION OFFICE OF ALAMINOS CITY | [11 empty] | Procurement Monitoring Report as of month/day/year
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of Materials for the repainting of SDO grounds, canopies, Admin. Office and replacement of door jamb at SMME Office | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 18-01-2023 | 18-01-2023 |  | 18-01-2023 | 18-01-2023 | 18-01-2023 |  |  |  | 18-01-2023 | 23-01-2023 | 20-01-2023 |  |  | 24-01-2023 | 25-01-2023 | Government of the Philippines (current year's budget) | 26025 | 26025 |  | 20690 | 20690 |  | 0.205 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA242 - Disaster Preparedness and Response Program | Procurement of snacks for the conduct of SDO Alaminos City Mangrove Tree Planting at Bued Mangrove Park | School Governance and Operations Division - DRRM | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-01-17 | 2023-01-17 |  | 2023-01-18 | 2023-01-18 | 2023-01-18 |  |  |  | 2023-01-18 | 2023-01-20 | 2023-02-02 |  |  | 2023-02-24 | 2023-02-24 | Government of the Philippines (current year's budget) | 7500 | 7500 |  | 7500 | 7500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of office and other supplies for SDO Alaminos City | Office of the Schools Division Superintendent | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 24-01-2023 | 24-01-2023 |  | 24-01-2023 | 24-01-2023 | 24-01-2023 |  |  |  | 24-01-2023 | 30-01-2023 | 24-01-2023 |  |  | 2023-01-27 | 2023-01-27 | Government of the Philippines (current year's budget) | 109122 | 109122 |  | 88611 | 88611 |  | 0.18796 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of labor and aterials for the fabrication of file cabinet at the SDS Office and key box cabinet for security purposes | Office of the Schools Division Superintendent | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-01-26 | 2023-01-27 |  | 2023-01-27 | 2023-01-27 | 2023-01-27 | 0 | 0 |  | 2023-01-27 | 2023-01-27 | 2023-01-27 | 0 |  | 2023-02-14 | 2023-02-14 | Government of the Philippines (current year's budget) | 25000 | 25000 |  | 24850 | 24850 |  | 0.006 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of medicines and medical supplies for the medical, nursing and dental health servuces for all personnel of SDO Alaminos City | Office of the Schools Division Superintendent | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-01-27 | 2023-01-27 |  | 2023-01-27 | 2023-01-27 | 2023-01-27 |  |  |  | 2023-01-27 | 2023-01-27 | 2023-01-27 |  |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 33801 | 33801 |  | 33801 | 33801 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA106 - General Management and Supervision - Division Office - Proper | Labor and materials for the repair and maintenance of division vehicle L300 with plate number SHV492 | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-01-30 |  |  |  | 2023-01-30 | 2023-01-30 | 2023-01-30 | 0 |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 36000 | 36000 |  | 36000 | 36000 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of training materials for the conduct of Division Staff Orientation Workshop (DSOW) on Division Training workshop on job embedded learning for teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-02 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 | 0 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 |  | 2023-02-02 | 2023-02-02 | Government of the Philippines (current year's budget) | 7100 | 7100 |  | 5847 | 5847 |  | 0.17648 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of meals and snacks for the conduct of Division Staff Orientation Workshop (DSOW) on the conduct of Division training/workshop on job embedded learning for teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-02 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  |  | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 12500 | 12500 |  | 12375 | 12375 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of training materials for the conduct of Division Staff orientation workshop (DSOW) on capacity building of teachers on creating happy, effective and productive connections through Socio-emotional Learning (SEL) | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-02 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 | 0 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 |  | 2023-02-02 | 2023-02-02 | Government of the Philippines (current year's budget) | 8100 | 8100 |  | 7678 | 7678 |  | 0.052099 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of meals ( breakfast, lunch, and dinner) and snacks (AM & PM) with training venue for 3 days for the conduct of Division Training Workshop on Job Embedded Learning for Teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-01 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 | 0 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 327600 | 327600 |  | 326235 | 326235 |  | 0.0041667 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of meals (breakfast, lunch, and dinner) and snacks (AM & PM) with training venue for 3 days for the conduct of capacity builiding of teachers on creating happy, effective and productive connections through Socioemotional Learning (SEL) | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-01 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 | 0 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 327600 | 327600 |  | 326235 | 326235 |  | 0.0041667 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA370 - Human resource development for personnel in schools and learning centers | Procurements of meals and snacks (AM & PM) for 3 days for the conduct of division staff orientation workshop (DSOW) on capacity building of teachers on creating happy, effective and productive connections through Socio-emotional Learning (SEL) | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-02 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 | 0 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 | 0 |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 40500 | 40500 |  | 40095 | 40095 |  | 0.01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of training materials for the conduct of capacity building of teachers on creating happy, effective and productive connections through Socio-emotional Learning (SEL) | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-02 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  |  | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 22800 | 22800 |  | 21211 | 21211 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of training materials for the conduct of Division training/workshop on job embedded learning for teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-02 | 2023-02-02 |  | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  |  | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  | 2023-02-03 | 2023-02-03 | Government of the Philippines (current year's budget) | 22800 | 22800 |  | 18071 | 18071 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of training materials for the conduct of Pedagogical Retooling in Teaching Reading Grade 4-12 English and Filipino teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-06 | 2023-02-07 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 |  |  |  | 2023-02-07 | 2023-02-07 | 2023-02-07 |  |  | 2023-02-09 | 2023-02-09 | Government of the Philippines (current year's budget) | 38700 | 38700 |  | 35126 | 35126 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of lunch and snacks (AM & PM) with training venue for 3 days for the conduct of Pedagogical Retooling in teaching reading for grades 4-12 English and Filipino teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-06 | 2023-02-07 |  | 2023-02-07 | 2023-02-07 | 2023-02-07 |  |  |  | 2023-02-07 | 2023-02-07 | 2023-02-07 |  |  | 2023-02-09 | 2023-02-09 | Government of the Philippines (current year's budget) | 333600 | 333600 |  | 331515 | 331515 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of meals and snacks (AM & PM) for 4 days for the conduct of planning workshop on Strategic Learning Action Cell (LAC) Sessions and other Professional development activities of teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-10 | 2023-02-13 |  | 2023-02-13 | 2023-02-13 | 2023-02-13 |  |  |  | 2023-02-13 | 2023-02-13 | 2023-02-13 |  |  | 2023-02-16 | 2023-02-16 | Government of the Philippines (current year's budget) | 78000 | 78000 |  | 77220 | 77220 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA370 - Human resource development for personnel in schools and learning centers | Procurement of training materials for the conduct of planning workshop on strategic learning action cell (LAC) sessions and other Professional Development Action for Teachers | Curriculum Implementation Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-08 | 2023-02-09 |  | 2023-02-09 | 2023-02-09 | 2023-02-09 |  |  |  | 2023-02-09 | 2023-02-09 | 2023-02-09 |  |  | 2023-02-13 | 2023-02-13 | Government of the Philippines (current year's budget) | 9800 | 9800 |  | 9240 | 9240 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Labor and materials for the repair and maintenance of division vehicle Mitsubishi Strada | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-02-15 |  |  |  | 2023-02-15 | 2023-02-15 | 2023-02-15 |  |  | 2023-02-17 | 2023-02-17 | Government of the Philippines (current year's budget) | 10297 | 10297 |  | 10297 | 10297 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Labor and materials for therepair ad maintenance of division vehicle Toyota Hi-ace van with plate number PZ189 | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-02-15 |  |  |  | 2023-02-15 | 2023-02-15 | 2023-02-15 |  |  | 2023-02-17 | 2023-02-17 | Government of the Philippines (current year's budget) | 35785 | 35785 |  | 35785 | 35785 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of office supplies for commission on audit (COA) use | Office of the Schools Division Superintendent | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | N/A |  | N/A | 2023-02-20 | 2023-02-20 |  | 21-02-2023 | 21-02-2023 | 21-02-2023 |  |  |  | 21-02-2023 | 2023-02-23 | 21-02-2023 |  |  | 2023-02-27 | 2023-02-27 | Government of the Philippines (current year's budget) | 37079.7 | 37079.7 |  | 33997.5 | 33997.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of SDO office supplies and equipment for the month of February, 2023 | Office of the Schools Division Superintendent | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-02-20 | 2023-02-27 |  | 2023-02-27 | 2023-02-27 | 2023-02-27 |  |  |  | 2023-02-27 | 2023-02-27 | 2023-02-27 |  |  | 2023-03-01 | 2023-03-01 | Government of the Philippines (current year's budget) | 294848.5 | 294848.5 |  | 262438 | 262438 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement and delivery of electrical and plumbing materials for the SDO Offices | Office of the Schools Division Superintendent | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-03-08 | 2023-03-09 |  | 2023-03-09 | 2023-03-09 | 2023-03-10 |  |  |  | 2023-03-13 | 2023-03-17 | 2023-03-17 |  |  | 2023-03-17 | 2023-03-17 | Government of the Philippines (current year's budget) | 6531 | 6531 |  | 6530 | 6530 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procuement of SDO office supplies and equipment for the month of March, 2023 | Office of the Schools Division Superintendent | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-03-28 | 2023-03-28 |  | 2023-03-28 | 2023-03-28 | 2023-03-28 |  |  |  | 2023-03-28 | 2023-03-29 | 2023-03-29 |  |  | 2023-03-31 | 2023-03-31 | Government of the Philippines (current year's budget) | 130205 | 130205 |  | 125065 | 125065 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA201 - Physical Fitness and School Sports | Procurement of Sports supplies and equipment for Division Meet (2nd Wave) | School Governance and Operations Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-03-20 | 2023-03-20 |  | 2023-03-20 | 2023-03-20 | 2023-03-20 |  |  |  | 2023-03-21 | 2023-03-21 | 2023-03-21 |  |  | 2023-03-24 | 2023-03-24 | Government of the Philippines (current year's budget) | 49980 | 49980 |  | 48300 | 48300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA201 - Physical Fitness and School Sports | Procuremet of meals and snacks for Division Meet (2nd Wave) | School Governance and Operations Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-03-20 | 2023-03-20 |  | 2023-03-20 | 2023-03-20 | 2023-03-20 | 0 | 0 |  | 2023-03-21 | 2023-03-21 | 2023-03-21 | 0 |  | 2023-03-23 | 2023-03-23 | Government of the Philippines (current year's budget) | 49922 | 49922 |  | 49235 | 49235 |  | 0.013761 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA201 - Physical Fitness and School Sports | Procurement of Plastic Square divided lunch boxes for Division Meet (2nd Wave) | School Governance and Operations Division | No | NP-53.10 - Small Value Procurement | N/A | N/A |  | N/A | 2023-03-20 | 2023-03-20 |  | 2023-03-20 | 2023-03-20 | 2023-03-20 | 0 | 0 |  | 2023-03-21 | 2023-03-21 | 2023-03-21 | 0 |  | 2023-03-24 | 2023-03-24 | Government of the Philippines (current year's budget) | 48000 | 48000 |  | 47520 | 47520 |  | 0.01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA106 - General Management and Supervision - Division Office - Proper | Labor and materials for the repair and maintennace of division vehicle - Toyota Avanza with plate number SHV442 | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-03-22 |  |  |  | 2023-03-22 | 2023-03-22 | 2023-03-22 | 0 |  | 2023-03-24 | 2023-03-24 | Government of the Philippines (current year's budget) | 10700 | 10700 |  | 10700 | 10700 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of labor and materials for the repair and maintenance of divison vehicle - Toyota Hi-ace van with plate number P5Z189 | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-03-22 |  |  |  | 2023-03-28 | 2023-03-28 | 2023-03-28 | 0 |  | 2023-04-03 | 2023-04-03 | Government of the Philippines (current year's budget) | 5270 | 5270 |  | 5270 | 5270 |  | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
PPA106 - General Management and Supervision - Division Office - Proper | Procurement and delivery of office table and filing cabinets for OSDS (SDS Office, ICT & Property Unit) SGOD and CID | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-04-17 | 2023-04-17 |  | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  |  | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  | 2023-04-20 | 2023-04-20 | Government of the Philippines (current year's budget) | 78200 | 78200 |  | 78015 | 78015 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurements and delivery of Medical Supplies and Medicines for Medical, Nursing, and Dental Services for SDO Personnel for the 2nd quarter | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-04-17 | 2023-04-17 |  | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  |  | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  | 2023-04-20 | 2023-04-20 | Government of the Philippines (current year's budget) | 28000 | 28000 |  | 27277 | 27277 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA371 - Human resource development for personnel in schools and learning centers | Procurement and delivery of training materials/supplies for School Leadership Development Program Course 2 & 3 | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-04-17 | 2023-04-17 |  | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  |  | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  | 2023-04-21 | 2023-04-21 | Government of the Philippines (current year's budget) | 50000 | 50000 |  | 45936 | 45936 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Installation of alarm and power lock for Division Vehicle Toyota Hi-Ace van with the plate no. P5Z189 | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-04 | 2023-05-04 |  | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  |  | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  | 2023-04-11 | 2023-04-11 | Government of the Philippines (current year's budget) | 7470 | 7470 |  | 7470 | 7470 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA371 - Human resource development for personnel in schools and learning centers | Procurement and delivery of training materials for the division staff orientation workshop for leadership program: Managing the Schools effectively (Phase 1 and Phase 2) | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-04 | 2023-05-04 |  | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  |  | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  | 2023-04-11 | 2023-04-11 | Government of the Philippines (current year's budget) | 9000 | 9000 |  | 8302 | 8302 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA371 - Human resource development for personnel in schools and learning centers | Meals and snacks for the Division Staff Orientation Workshop for Leadership Program: Managing the schools effectively (Phase 1 & 2) | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-04 | 2023-05-04 |  | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  |  | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  | 2023-04-12 | 2023-04-12 | Government of the Philippines (current year's budget) | 15000 | 15000 |  | 14850 | 14850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement and delivery os SDO supplies and other materials for the months of April and May, 2023 | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-12 | 2023-05-12 |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  | 2023-05-15 | 2023-05-15 | Government of the Philippines (current year's budget) | 144187.2 | 144187.2 |  | 143586.5 | 143586.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement, delivery, and installation of air-conditioning unit at the SDO Medical and CID offices | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-12 | 2023-05-12 |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  | 2023-05-15 | 2023-05-15 | Government of the Philippines (current year's budget) | 64000 | 64000 |  | 60120.64 | 60120.64 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA366 - Madrasah Education Program | Procurement and delivery of meals and snacks for the conduct of symposium with muslim parents and stakeholders on Madrasah Education Program | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-12 | 2023-05-12 |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  | 2023-05-17 | 2023-05-17 | Government of the Philippines (current year's budget) | 12500 | 12500 |  | 12375 | 12375 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Repair and maintenance of air-conditioning units of offices in the SDO | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-12 | 2023-05-12 |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  |  | 2023-05-12 | 2023-05-12 | 2023-05-12 |  |  | 2023-05-16 | 2023-05-16 | Government of the Philippines (current year's budget) | 41600 | 41600 |  | 36750 | 36750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA371 - Human resource development for personnel in schools and learning centers | Procurement and delivery of meals and snacks for the 3 days with the venue and room accommdation for the conduct of School Leadeship Development Program Review and Evaluation | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-19 | 2023-05-19 |  | 2023-05-19 | 2023-05-19 | 2023-05-19 |  |  |  | 2023-05-19 | 2023-05-19 | 2023-05-19 |  |  | 2023-05-23 | 2023-05-23 | Government of the Philippines (current year's budget) | 210000 | 210000 |  | 209475 | 209475 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA104 - General Management and Supervision - Regional Office Proper | Procurement and delivery of meals,snacks (AM & PM) and room accommodation for hosting the 2023 Regional Schools Press Conference (RSPC) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-08 | 2023-06-08 |  | 2023-06-08 | 2023-06-08 | 2023-06-08 |  |  |  | 2023-06-08 | 2023-06-08 | 2023-06-08 |  |  | 2023-06-13 | 2023-06-13 | Government of the Philippines (current year's budget) | 300000 | 300000 |  | 289000 | 289000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA385 - Flexible Learning Options (ADM/ALS/EiE) | Procurement and delivery of meals (lunch) for 4 days for the conduct of LAC Session on enhancing digital citizenship (LS6) through mobile technology for ALS teachers | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-23 | 2023-05-23 |  | 2023-05-23 | 2023-05-23 | 2023-05-23 |  |  |  | 2023-05-23 | 2023-05-23 | 2023-05-23 |  |  | 2023-05-25 | 2023-05-25 | Government of the Philippines (current year's budget) | 13200 | 13200 |  | 13090 | 13090 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Replacement of brake pad (Toyota Avanza) and replacement of tire (L300) | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-05-25 |  |  |  | 2023-05-25 | 2023-05-25 | 2023-05-25 |  |  | 2023-05-26 | 2023-05-26 | Government of the Philippines (current year's budget) | 24850 | 24850 |  | 24850 | 24850 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Replacement of damage electric meter base at SDO Building 2 | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-05-25 | 2023-05-25 |  | 2023-05-25 | 2023-05-25 | 2023-05-25 |  |  |  | 2023-05-25 | 2023-05-25 | 2023-05-25 |  |  | 2023-05-29 | 2023-05-29 | Government of the Philippines (current year's budget) | 11982 | 11982 |  | 11982 | 11982 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Supply and delivery of purified mineral drinking water for SDO Personnel from June to December, 2023 | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-02 | 2023-06-02 |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  | 2023-06-06 | 2023-06-06 | Government of the Philippines (current year's budget) | 17150 | 17150 |  | 14700 | 14700 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of repair and maintenance of Division vehicle Toyota Hi-Ace van with plate number P5Z189 (perform 110,00km check-up) | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-05-26 |  |  |  | 2023-05-26 | 2023-05-26 | 2023-05-26 |  |  | 2023-05-29 | 2023-05-29 | Government of the Philippines (current year's budget) | 19925 | 19925 |  | 19925 | 19925 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA104 - General Management and Supervision - Regional Office Proper | Procurement and delivery of medicines for the conduct of 2023 Regional Schools Press Conference 2023 | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-02 | 2023-06-02 |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  | 2023-06-05 | 2023-06-05 | Government of the Philippines (current year's budget) | 4280 | 4280 |  | 4260 | 4260 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA104 - General Management and Supervision - Regional Office Proper | Procurement and delivery of medals and trophies for the conduct of 2023 Regional School Press Conference (RSPC) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-02 | 2023-06-02 |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  | 2023-06-06 | 2023-06-06 | Government of the Philippines (current year's budget) | 70000 | 70000 |  | 70000 | 70000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA104 - General Management and Supervision - Regional Office Proper | Procurement and delivery of customized t-shirts for DepEd Top Officials during the conduct of 2023 Regional Schools Press Conference (RSPC) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-02 | 2023-06-02 |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  | 2023-06-06 | 2023-06-06 | Government of the Philippines (current year's budget) | 56100 | 56100 |  | 56100 | 56100 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA104 - General Management and Supervision - Regional Office Proper | Procuremet and delivery of supplies and materials for hosting the 2023 Regional Schools Press Conference (RSPC) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-02 | 2023-06-02 |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  |  | 2023-06-02 | 2023-06-02 | 2023-06-02 |  |  | 2023-06-05 | 2023-06-05 | Government of the Philippines (current year's budget) | 21620 | 21620 |  | 20183 | 20183 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of materials for the repainting of entrance/exit gates and bulletin board at the Administrative Office | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-08 | 2023-06-08 |  | 2023-06-08 | 2023-06-08 | 2023-06-08 |  |  |  | 2023-06-08 | 2023-06-08 | 2023-06-08 |  |  | 2023-06-13 | 2023-06-13 | Government of the Philippines (current year's budget) | 8040 | 8040 |  | 6900 | 6900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement and delivery of sliding windows for the repair of Division Vehicle(L300) and the clear glass for the replacement of bulletin Board sliding glass | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-06-20 | 2023-06-20 |  |  |  | 2023-06-20 | 2023-06-20 | 2023-06-20 |  |  | 2023-06-26 | 2023-06-26 | Government of the Philippines (current year's budget) | 6600 | 6600 |  | 6500 | 6500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA103 - General Management and Supervision - Regional Office Proper | Procurement and delivery of meals (breakfast, lunch, and dinner) and snacks (AM & PM)of jugdes for the 2023 Regional Schools Press Conference RSPC | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-13 | 2023-06-13 |  | 2023-06-13 | 2023-06-13 | 2023-06-13 |  |  |  | 2023-06-13 | 2023-06-13 | 2023-06-13 |  |  | 2023-06-16 | 2023-06-16 | Government of the Philippines (current year's budget) | 18000 | 18000 |  | 17925 | 17925 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of the replacement of Division vehicle Toyota Avanza battery and air cleaner with plate number SHV442 | Office of the Schools Division Superintendent | No | Direct Contracting | N/A | N/A |  | N/A | N/A | N/A |  | N/A | N/A | 2023-06-14 |  |  |  | 2023-06-14 | 2023-06-14 | 2023-06-14 |  |  | 2023-06-20 | 2023-06-20 | Government of the Philippines (current year's budget) | 7900 | 7900 |  | 7900 | 7900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement and delivery of building marker for the newly constructed SDO Two-storey Multi-Purpose Building | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-20 | 2023-06-20 |  | 2023-06-20 | 2023-06-20 | 2023-06-20 |  |  |  | 2023-06-20 | 2023-06-21 | 2023-06-21 |  |  | 2023-06-26 | 2023-06-26 | Government of the Philippines (current year's budget) | 12300 | 12300 |  | 12000 | 12000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Replacement of battery for the division vehicle L300 with plate number SHV492 | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-06-29 | 2023-06-29 |  | 2023-06-29 | 2023-06-29 | 2023-06-29 |  |  |  | 2023-06-29 | 2023-06-29 | 2023-06-29 |  |  | 2023-07-03 | 2023-07-03 | Government of the Philippines (current year's budget) | 9400 | 9400 |  | 9400 | 9400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA384 - Flexible Learning Options (ADM/ALS/EiE) | Procurement of Lunch and Snacks for the DSOW on Division Training Workshop on Capacitating ALS Teachers in Teaching Beginning Reading and Least Mastered Skills (LS1 and LS3) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-05 | 2023-07-05 |  | 2023-07-05 | 2023-07-05 | 2023-07-05 |  |  |  | 2023-07-07 | 2023-07-10 | 2023-07-10 |  |  | 2023-07-07 | 2023-07-07 | Government of the Philippines (current year's budget) | 10000 | 10000 |  | 9900 | 9900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA384 - Flexible Learning Options (ADM/ALS/EiE) | Procurement of Lunch and Snacks on the conduct of Division Training Workshop on Capacitating ALS Teachers in Teaching Beginning Reading and Least Mastered Skills (LS1 and LS3) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 |  |  |  | 2023-07-07 | 2023-07-10 | 2023-07-10 |  |  | 7/12-14/2023 | 7/12-14/2023 | Government of the Philippines (current year's budget) | 55200 | 55200 |  | 54510 | 54510 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA384 - Flexible Learning Options (ADM/ALS/EiE) | Procurement of training materials for the Division Training Workshop on Capacitating ALS Teachers in Teaching Beginning Reading and Least Mastered Skills (LS1 and LS3) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 |  |  |  | 2023-07-07 | 2023-07-10 | 2023-07-10 |  |  | 2023-07-11 | 2023-07-11 | Government of the Philippines (current year's budget) | 3900 | 3900 |  | 3632 | 3632 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA371 - Human resource development for personnel in schools and learning centers | Procurement of Training Venue, Meals (Breakfast, Lunch and Dinner), Snacks (AM & PM), and Room Accommodation for the Conduct of School Leadership Development Program (SLDP) Courses 2 & 3 | School Governance and Operations Division - HRD | No | Competitive Bidding | 2023-04-03 | 2023-04-04 |  | 2023-04-12 | 2023-04-25 | 2023-04-25 |  | 2023-04-25 | 2023-04-25 | 2023-04-27 |  |  |  | 2023-04-27 | 2023-04-28 | 2023-04-29 |  |  | 5/2-6/2023 and 5/22-26/2023 | 5/2-6/2023 and 5/22-26/2023 | Government of the Philippines (current year's budget) | 1740000 | 1740000 |  | 1735650 | 1735650 |  |  | COA, member of Philippine Chamber of Commerce and Industry, chairman of a civic society organization (NGO) | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2023-04-25 | 5/2-6/2023 and 5/22-26/2023
PPA629 - SPF - QRF - National Disaster Risk Reduction and Management Fund (Calamity Fund) | Repair of Classrooms (Gabaldon Building) at Alaminos Central School | Alaminos Central School | Yes | Competitive Bidding | 2023-03-10 | 2023-03-14 |  | 2023-03-22 | 2023-04-04 | 2023-04-04 |  | 2023-04-04 | 2023-04-11 | 2023-04-14 |  |  |  | 2023-04-17 | 2023-04-18 | 2023-04-19 |  |  | 220 days |  | Government of the Philippines (current year's budget) | 28000000 | 28000000 |  | 27723177.18 | 27723177.18 |  |  | COA, member of national associations of constructors, chairman of a civic society organization (NGO) | 2023-03-14 | 2023-03-14 | 2023-03-14 | 2023-03-14 | 2023-04-04 | 220 days
-
[25 empty] | Total Allotted Budget of Procurement Activities | 33215570.4 | 33215570.4 | 0 |  |  |  | 1.211%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 32813178.82 | 32813178.82 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 402391.58 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
PPA384 - Flexible Learning Options (ADM/ALS/EiE) | Procurement of Lunch and Snacks for the DSOW on Division Training Workshop On Fundamental Computer Operations And Digital Literacy (LS6) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 | 0 |  | 2023-07-07 | 2023-07-10 | 2023-07-10 | 3 |  |  |  | Government of the Philippines (current year's budget) | 10000 | 10000 |  | 9900 | 9900 |  | 0.01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0
PPA384 - Flexible Learning Options (ADM/ALS/EiE) | Procurement of Lunch and Snacks on the conduct of Division Training Workshop on Fundamental Computer Operations and Digital Literacy (LS6) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 | 0 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 |  |  |  | Government of the Philippines (current year's budget) | 55200 | 55200 |  | 54510 | 54510 |  | 1.25% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0
PPA371 - Human resource development for personnel in schools and learning centers | Procurement of Training Paraphernalia for Human Resource Development | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 | 0 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 |  |  |  | Government of the Philippines (current year's budget) | 13776.44 | 13776.44 |  | 13690 | 13690 |  | 0.6274% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0
PPA371 - Human resource development for personnel in schools and learning centers | Procurement of Training Paraphernalia for Human Resource Development | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 | 0 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 |  |  |  | Government of the Philippines (current year's budget) | 12963.68 | 12963.68 |  | 12901.68 | 12901.68 |  | 0.0047826 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0
PPA384 - Flexible Learning Options (ADM/ALS/EiE) | Procurement of training materials for the Division Training Workshop on Fundamental Computer Operations and Digital Literacy (LS6) | Curriculum Implementation Division | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 0 | 0 |  | 2023-07-10 | 2023-07-10 | 2023-07-10 | 0 |  | 2023-07-11 | 2023-07-11 | Government of the Philippines (current year's budget) | 3900 | 3900 |  | 3632 | 3632 |  | 0.068718 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of SDO supplies for the month of July, 2023 | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 |  |  |  | 2023-07-07 | 2023-07-10 | 2023-07-10 |  |  |  |  | Government of the Philippines (current year's budget) | 108455 | 108455 |  | 105367 | 105367 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA371 - Human resource development for personnel in schools and learning centers | Procurement of meals and snacks with training venue on the conduct of the 3-Day Leadership Program: Managing The Schools Effectively – Phase 1 | School Governance and Operations Division - HRD | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 |  |  |  | 2023-07-07 | 2023-07-10 | 2023-07-10 |  |  |  |  | Government of the Philippines (current year's budget) | 270000 | 270000 |  | 269100 | 269100 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPA106 - General Management and Supervision - Division Office - Proper | Procurement of Digital-Type Photo Printing with Wooden Frame and glass cover for the Awareness And Appreciation of the Achievements And Leadership of the previous and present SDS and ASDS of the division | Office of the Schools Division Superintendent | No | NP-53.9 - Small Value Procurement | N/A | N/A |  | N/A | 2023-07-07 | 2023-07-07 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 |  |  |  | 2023-07-07 | 2023-07-10 | 2023-07-10 |  |  |  |  | Government of the Philippines (current year's budget) | 14950 | 14950 |  | 14950 | 14950 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
-
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 489245.12 | 489245.12 | 0 | 484050.68 | 484050.68 | 0 | 2.046%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | ROBE ROSE S. GUBATAN | [9 empty] | MARILU N. CARDENAS | [16 empty] | VIVIAN LUZ S. PAGATPATAN, CESO VI
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 33153931
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 66
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.083333 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.020833 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 2 | 2 | 29740000 | 29458827.18 | 100% | 99.05% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 8 | 8 | 150727 | 150727 | 100% | 100% | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2 | 0 | 0 | 0 | 0% |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 36 | 35 | 1766974.32 | 1728289.82 | 97.22% | 97.81% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 48 | 45 | 31657701.32 | 31657701.32 | 74.31% | 98.96% | 0 | 0
Total for Alternative Mode of Procurement | 46 | 43 | 1917701.32 | 1879016.82 | 65.74% | 98.91% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Completed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Failed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Ongoing | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Total | 0 | 0% | 0 | 0% | 0 | #DIV/0! | #DIV/0!
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 1.449%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 83.07%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 1 | 28000000
Regular Procurement | 68 | 5704815.52
Total | 69 | 33704815.52
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 1 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell